## Sheet1
Attachment Information Sheet - Revision 10/10/2022
Project No# | 5519587 | H1014
Application #
License #
Location | Butte, MT
Attachment Total | 43
Responsible Engineer | Jared Kariniemi
Contact Info | jared@bookereng.com
Pole Number | Latitude | Longitude | Pole Ht/ Class | Span Length | Pole Owner | Proposed Riser (Yes/No) & Qty | Proposed Guy (Yes/No) & Qty | Existing Loading | Proposed Loading | Construction Grade of Analysis | Make Ready Data | [6 empty] | Communication Make Ready | Utility Make Ready | Pole Replacement | Pole Replacement Responsibility | Notes | Additional Notes
[11 empty] | Attacher Description | Attachment Height |  | Midspan | Mid-Span (only if wire is being moved) Field Temp | Worse Case (Wire-Wire) Primary-167°F , Neutral & Secondary 120°F , Comm -104°F | Lowest Comm Max Sag Ground Clearance (Hot 104°F OR 32°F with .25" ice)
[12 empty] | Existing | Proposed | Existing
1-1 | 46.0096 | -112.5385 | 40/5 | 132' N 85' S | NWE | No | No | 51.9% | 63.8% | C | NWE Primary Crossarm (N) | 33' 6" |  | 33' 8" |  | 32' 7" | 33' 3" | Lower Lumen to 17'9" Attach Ziply at 18'9" | "Raise secondary riser to 23'6""
[11 empty] | NWE Primary Crossarm (S) | 33' 6" |  | 33' 4" |  | 33' 4" | 33' 10"
[11 empty] | NWE Top Transformer | 29' 9"
[11 empty] | NWE Base Transformer | 26' 9"
[11 empty] | NWE Neutral (N) | 24' 9" |  |  |  | 23' 7" | 23' 8"
[11 empty] | NWE Secondary Drop (N) | 24' 9" |  | 25' 10" |  | 23' 2" | 24' 0"
[11 empty] | NWE Secondary Drop (S) | 24' 9" |  | 24' 8" |  | 24' 1" | 24' 7"
[11 empty] | Drip Loop | 23' 6"
[11 empty] | NWE Riser | 21' 11" | 23' 6"
[11 empty] | Spectrum CATV (N) | 19' 10" |  | 21' 5" | 19' 9" | 19' 7" | 19' 4"
[11 empty] | Spectrum CATV (S) | 19' 10" |  | 20' 0" | 19' 10" | 19' 10" | 19' 10"
[11 empty] | Ziply Fiber (N) |  | 18' 9" |  | 18' 7" | 18' 6" | 18' 4"
[11 empty] | Ziply Fiber (S) |  | 18' 9" |  | 18' 9" | 18' 9" | 18' 9"
[11 empty] | Lumen (N) | 19' 3" | 17' 9" | 18' 5" | 17' 5" | 17' 3" | 17' 0"
[11 empty] | Lumen (S) | 19' 3" | 17' 9" | 17' 7" | 17' 9" | 17' 9" | 17' 8"
1-2 | 46.0093 | -112.5385 | 40/5 | 101' E 86' S | NWE | No | No | 48% | 52.4% | C | NWE Primary Crossarm | 33' 7" |  | 32' 1" |  | 33' 3" | 33' 10" | "Raise Spectrum to 21'6" Attach Ziply at 20'6"
[11 empty] | NWE Top Transformer | 31' 3"
[11 empty] | NWE Base Transformer | 28' 7"
[11 empty] | NWE Secondary Drop | 27' 5" |  | 18' 11" |  | 26' 2" | 27' 0"
[11 empty] | Drip Loop | 26' 3"
[11 empty] | Spectrum CATV | 20' 5" | 21' 6" | 20' 8" | 21' 6" | 21' 6" | 21' 5"
[11 empty] | Ziply Fiber (E) |  | 20' 6" |  | 19' 0" | 19' 0" | 18' 11"
[11 empty] | Ziply Fiber (S) |  | 20' 6" |  | 20' 6" | 20' 6" | 20' 5"
[11 empty] | Lumen | 19' 1" |  | 18' 6" | 19' 1" | 19' 1" | 19' 1"
1-3 | 46.0091 | -112.5385 | 40/4 | 79' | NWE | No | No | 20% | 23.9% | C | NWE Primary Crossarm | 33' 5" |  | 33' 5" |  | 33' 2" | 33' 8" | "Raise Spectrum to 22'7" Attach Ziply at 21'7"
[11 empty] | Spectrum CATV | 21' 7" | 22' 7" | 20' 3" | 21' 2" | 21' 2" | 21' 2"
[11 empty] | Ziply Fiber |  | 21' 7" |  | 20' 2" | 20' 2" | 20' 2"
[11 empty] | Lumen | 20' 9" |  | 19' 3" |  | 18' 10" | 18' 9"
1-4 | 46.0089 | -112.5384 | 40/5 | 127' | NWE | No | No | 21.7% | 24.4% | C | NWE Primary Crossarm | 33' 2" |  | 34' 1" |  | 32' 8" | 33' 3" | "Raise Spectrum to 21'2" Attach Ziply at 20'2" Retension and Sag Spectrum.
[11 empty] | NWE Crossarm | 30' 1"
[11 empty] | NWE Secondary Drop | 25' 0" |  | 22' 10" |  | 23' 9" | 24' 6"
[11 empty] | NWE Riser | 24' 11"
[11 empty] | Street Light | 24' 7"
[11 empty] | Spectrum CATV | 19' 8" | 21' 2" | 20' 5" | 21' 0" | 20' 10" | 20' 8"
[11 empty] | Ziply Fiber |  | 20' 2" |  | 19' 11" | 19' 10" | 19' 7"
[11 empty] | Lumen | 18' 10" |  | 20' 0" | 18' 6" | 18' 4" | 18' 2"
[11 empty] | Spectrum Riser | 18' 4"
1-5 | 46.0085 | -112.5384 | 40/6 | 94' E 75' S | NWE | No | No | 48.4% | 54.5% | C | NWE Primary Crossarm | 33' 6" |  | 33' 2" |  | 33' 4" | 33' 10" | "Lower Lumen to 19'5"" Attach Ziply at 20'5"" | Dress secondary drip loop
[11 empty] | NWE Top Transformer | 32' 2"
[11 empty] | NWE Base Transformer | 29' 2"
[11 empty] | NWE Secondary Crossarm | 27' 8" |  | 26' 10" |  | 27' 6" | 27' 5"
[11 empty] | NWE Downguy | 27' 2"
[11 empty] | NWE Secondary Drop | 26' 4" |  | 18' 10" |  | 23' 7" | 24' 2"
[11 empty] | Drip Loop | 24' 6"
[11 empty] | Street Light (x2) | 25' 7"
[11 empty] | Street Light Drip | 24' 9"
[11 empty] | Spectrum CATV | 21' 7" |  | 21' 4" | 21' 6" | 21' 5" | 21' 4"
[11 empty] | Ziply Fiber (E) |  | 20' 5" |  | 18' 0" | 18' 0" | 18' 0"
[11 empty] | Ziply Fiber (S) |  | 20' 5" |  | 20' 4" | 20' 4" | 20' 3"
[11 empty] | Lumen | 20' 5" | 19' 5" | 20' 3" | 19' 3" | 19' 3" | 19' 2"
[11 empty] | Lumen Riser | 19' 5"
1-6 | 46.0083 | -112.5384 | 40/5 | 100' | NWE | No | No | 29.4% | 31.6% | C | NWE Primary Crossarm | 33' 3" |  | 33' 1" |  | 32' 2" | 32' 8" | "Lower Lumen to 19'8"" Attach Ziply at 20'8" Retension and Sag Spectrum.
[11 empty] | NWE Secondary Crossarm | 28' 3" |  | 26' 10" |  | 27' 0" | 26' 10"
[11 empty] | Crossarm Brace | 26' 10"
[11 empty] | NWE Secondary Drop | 27' 2"
[11 empty] | Drip Loop | 26' 1"
[11 empty] | Spectrum CATV | 21' 8" |  | 20' 5" |  | 21' 0" | 20' 11"
[11 empty] | Ziply Fiber |  | 20' 8" |  | 20' 1" | 20' 0" | 19' 11"
[11 empty] | Lumen | 20' 8" | 19' 8" | 20' 0" | 19' 2" | 19' 1" | 18' 11"
1-7 | 46.0081 | -112.5383 | 40/4 | 91' E 105' S 72' W | NWE | No | No | 29.2% | 33.8% | C | NWE CrossarmSpan | 32' 11" | [5 empty] | "Lower Lumen to 19'2"" Attach Ziply at 20'2"" | Dress secondary drip loop"
[11 empty] | NWE Primary Crossarm | 32' 11" |  | 33' 0" |  | 32' 1" | 32' 6"
[11 empty] | NWE Top Transformer | 30' 1"
[11 empty] | NWE Base Transformer | 27' 1"
[11 empty] | NWE Secondary Crossarm | 26' 7" |  | 26' 6" |  | 26' 9" | 26' 6"
[11 empty] | Crossarm Brace | 25' 0"
[11 empty] | NWE Secondary Drop (E) | 25' 5" |  | 20' 1" |  | 25' 3" | 25' 6"
[11 empty] | NWE Secondary Drop (W) | 25' 5" |  | 22' 8" |  | 25' 4" | 25' 5"
[11 empty] | Drip Loop | 24' 0"
[11 empty] | Spectrum CATV | 21' 2" |  | 20' 4" |  | 20' 8" | 20' 6"
[11 empty] | Ziply Fiber (E) |  | 20' 2" |  | 18' 0" | 18' 0" | 18' 0"
[11 empty] | Ziply Fiber (S) |  | 20' 2" |  | 19' 5" | 19' 4" | 19' 3"
[11 empty] | Ziply Fiber (W) |  | 20' 2" |  | 18' 0" | 18' 0" | 18' 0"
[11 empty] | Lumen Vertical Standoff | 20' 2" | 19' 2" | 19' 11" | 18' 4" | 18' 3" | 18' 2"
1-8 | 46.0078 | -112.5383 | 40/5 | 81' | NWE | No | No | 32.7% | 36.5% | C | NWE Primary Crossarm | 32' 0" |  | 32' 8" |  | 32' 2" | 32' 7" | "Lower Lumen to 18'5"" Attach Ziply at 19'5"
[11 empty] | NWE Secondary Crossarm | 27' 0" |  | 27' 4" |  | 27' 5" | 27' 7"
[11 empty] | Crossarm Brace | 25' 7"
[11 empty] | NWE Secondary Drop | 25' 11"
[11 empty] | Drip Loop | 24' 8"
[11 empty] | NWE Span/Head | 21' 2"
[11 empty] | Spectrum CATV | 20' 10" |  | 20' 0" |  | 20' 6" | 20' 4"
[11 empty] | Ziply Fiber |  | 19' 5" |  | 19' 4" | 19' 3" | 19' 2"
[11 empty] | Lumen | 19' 11" | 18' 5" | 19' 5" | 18' 3" | 18' 2" | 18' 1"
1-9 | 46.0076 | -112.5382 | 40/5 | 85' S 99' NW | NWE | No | No | 36% | 39.2% | C | NWE Primary Crossarm | 32' 8" |  | 33' 1" |  | 32' 7" | 33' 1" | "Lower Lumen to 18'7"" Attach Ziply at 19'7"
[11 empty] | NWE Top Transformer | 31' 7"
[11 empty] | NWE Base Transformer | 28' 7"
[11 empty] | NWE Secondary Crossarm | 28' 0" |  | 27' 5" |  | 27' 0" | 26' 10"
[11 empty] | Crossarm Brace | 26' 8"
[11 empty] | NWE Secondary Drop | 26' 5" |  | 19' 9" |  | 21' 3" | 21' 6"
[11 empty] | Drip Loop | 25' 5"
[11 empty] | NWE Riser | 26' 0"
[11 empty] | Spectrum CATV | 20' 7" |  | 20' 5" | 20' 5" | 20' 4" | 20' 2"
[11 empty] | Ziply Fiber (S) |  | 19' 7" |  | 19' 4" | 19' 4" | 19' 3"
[11 empty] | Ziply Fiber (NW) |  | 19' 7" |  | 17' 0" | 17' 0" | 17' 0"
[11 empty] | Lumen | 19' 7" | 18' 7" | 19' 7" | 18' 3" | 18' 2" | 18' 1"
1-10 | 46.0073 | -112.5382 | 40/5 | 98' | NWE | No | No | 29.2% | 31.2% | C | NWE Primary Crossarm | 32' 10" |  | 32' 9" |  | 31' 7" | 32' 0" | "Lower Spectrum to 20'6"" Lower Lumen to 18'6"" Attach Ziply at 19'6"""
[11 empty] | NWE Top Transformer | 29' 10"
[11 empty] | NWE Base Transformer | 26' 10"
[11 empty] | NWE Secondary Crossarm | 26' 4" |  | 27' 9" |  | 26' 3" | 26' 1"
Crossarm Brace
[11 empty] | NWE Riser 1 | 24' 3"
[11 empty] | NWE Riser 2 | 24' 3"
[11 empty] | Spectrum CATV | 21' 10" | 20' 6" | 20' 9" | 20' 0" | 19' 10" | 19' 9"
[11 empty] | Ziply Fiber |  | 19' 6" |  | 18' 11" | 18' 10" | 18' 9"
[11 empty] | Lumen | 20' 6" | 18' 6" | 19' 8" | 17' 10" | 17' 9" | 17' 7"
1-11 | 46.0071 | -112.5382 | 40/5 | 127' | NWE | No | Yes/1 | 32% | 55.4% | C | NWE Primary Crossarm | 32' 3" |  | 29' 7" |  | 31' 2" | 31' 9" | "Attach Ziply strand and downguy at 19' Place Ziply anchor at 15' lead South and attach Ziply downguy. Move Lumen downguy to Ziply anchor"
[11 empty] | NWE Downguy | 31' 8"
[11 empty] | NWE Secondary Crossarm | 27' 0"
[11 empty] | Crossarm Brace | 25' 7"
[11 empty] | NWE Downguy | 26' 5"
[11 empty] | Spectrum CATV | 20' 0" |  | 20' 0" | 19' 11" | 19' 9" | 19' 6"
[11 empty] | Spectrum Downguy | 19' 11"
[11 empty] | Ziply Fiber |  | 19' 0" |  | 18' 10" | 18' 9" | 18' 7"
[11 empty] | Ziply Downguy |  | 19' 0"
[11 empty] | Lumen | 18' 0"
[11 empty] | Lumen Downguy | 18' 0"
1-12 | 46.0067 | -112.5383 | 40/5 | 108' S 81' SW | NWE | No | Yes/1 | 56.1% | 63.5% | C | NWE Primary Crossarm | 33' 6" |  | 31' 8" |  | 32' 4" | 32' 6" | "Attach Ziply strand and downguy at 19'9"" Attach Ziply downguy to existing Lumen anchor if capacity allows, else replace anchor"
[11 empty] | NWE Downguy | 32' 0"
[11 empty] | NWE Secondary Crossarm | 28' 5"
[11 empty] | Crossarm Brace | 26' 11"
[11 empty] | NWE Secondary Drop | 27' 4" |  | 23' 11" |  | 26' 0" | 26' 8"
[11 empty] | NWE Downguy | 27' 1"
[11 empty] | Spectrum CATV | 20' 9" |  | 20' 7" |  | 20' 6" | 20' 4"
[11 empty] | Spectrum CATV Downguy | 20' 9"
[11 empty] | Ziply Fiber (S) |  | 19' 9" |  | 19' 7" | 19' 6" | 19' 4"
[11 empty] | Ziply Fiber (SW) |  | 19' 9" |  | 17' 0" | 17' 0" | 17' 0"
[11 empty] | Ziply Fiber Downguy |  | 19' 9"
[11 empty] | Lumen | 18' 7" |  | 17' 9" | 17' 11" | 17' 10" | 17' 8"
[11 empty] | Lumen Downguy | 18' 7"
1-13 | 46.0064 | -112.5383 | 40/6 | 109' | NWE | No | No | 42.2% | 48.4% | C | NWE Primary Crossarm | 33' 1" |  | 31' 9" |  | 32' 5" | 33' 0" | Attach Ziply at 19'11"
[11 empty] | NWE Top Transformer | 31' 6"
[11 empty] | NWE Base Transformer | 28' 6"
[11 empty] | NWE Secondary Drop | 27' 5"
[11 empty] | Drip Loop | 26' 9"
[11 empty] | Spectrum CATV | 20' 11" |  | 20' 5" |  | 20' 9" | 20' 6"
[11 empty] | Ziply Fiber |  | 19' 11" |  | 19' 8" | 19' 7" | 19' 6"
[11 empty] | Lumen | 18' 2" |  | 18' 7" | 17' 11" | 17' 10" | 17' 8
1-14 | 46.0061 | -112.5383 | 40/5 | 116' | NWE | No | No | 43.2% | 47.3% | C | NWE Primary Crossarm | 33' 6" |  | 31' 8" |  | 32' 5" | 32' 8" | "Lower Lumen to 18'10"" Attach Ziply at 19'10"""
[11 empty] | NWE Secondary Crossarm | 26' 4" |  | 24' 0" |  | 25' 11" | 25' 9"
[11 empty] | Crossarm Brace | 24' 9"
[11 empty] | Spectrum CATV | 21' 3" |  | 19' 0" | 20' 10" | 20' 8" | 20' 6"
[11 empty] | Ziply Fiber |  | 19' 10" |  | 19' 8" | 19' 7" | 19' 6"
[11 empty] | Lumen | 20' 4" | 18' 10" | 17' 7" | 17' 11" | 17' 9" | 17' 7"
1-15 | 46.0058 | -112.5383 | 40/5 | 155' | NWE | No | No | 43.8% | 49.2% | C | NWE Primary Crossarm | 33' 11" |  | 29' 4" |  | 33' 6" | 33' 7" | "Raise Spectrum to 20'11"" Attach Ziply at 19'11"""
[11 empty] | NWE Top Transformer | 32' 3"
[11 empty] | NWE Base Transformer | 29' 3"
[11 empty] | NWE Secondary Crossarm | 27' 8" |  | 23' 5" |  | 27' 9" | 27' 4"
[11 empty] | Crossarm Brace | 26' 0"
[11 empty] | Spectrum CATV | 19' 11" | 20' 11" | 18' 0" | 19' 11" | 19' 8" | 19' 3"
[11 empty] | Ziply Fiber |  | 19' 11" |  | 18' 11" | 18' 10" | 18' 8"
[11 empty] | Lumen | 18' 2" |  | 15' 6" | 17' 2" | 16' 11" | 16' 7"
1-16 | 46.0054 | -112.5383 | 45/5 | 88' | NWE | No | No | 44% | 49% | C | NWE Primary Crossarm | 37' 6" |  | 33' 0" |  | 32' 10" | 32' 11" | Attach Ziply at 19'1"
[11 empty] | NWE Top Transformer | 35' 9"
[11 empty] | NWE Base Transformer | 32' 9"
[11 empty] | NWE Secondary Crossarm | 31' 3" |  | 27' 9" |  | 28' 2" | 28' 2"
[11 empty] | Crossarm Brace | 29' 10"
[11 empty] | Spectrum CATV | 20' 1" |  | 19' 7" | 19' 9" | 19' 8" | 19' 6"
[11 empty] | Ziply Fiber |  | 19' 1" |  | 18' 9" | 18' 8" | 18' 7"
[11 empty] | Lumen | 18' 1" |  | 18' 4" | 17' 7" | 17' 6" | 17' 5"
1-17 | 46.0052 | -112.5383 | 40/5 | 0' | NWE | No | Yes/1 | 36% | 43.7% | C | NWE Primary Crossarm | 32' 11" | [5 empty] | "Lower Lumen strand and downguy to 17'9"" Attach Ziply strand and downguy at 18'9"" Attach Ziply downguy to existing Lumen anchor if capacity allows, else replace anchor"
[11 empty] | NWE Downguy | 32' 2"
[11 empty] | NWE Secondary Crossarm | 28' 3"
[11 empty] | Crossarm Brace | 26' 10"
[11 empty] | NWE Downguy | 27' 4"
[11 empty] | Spectrum CATV | 19' 10"
[11 empty] | Spectrum CATV Downguy | 19' 10"
[11 empty] | Spectrum Riser | 19' 7"
[11 empty] | Ziply Fiber |  | 18' 9"
[11 empty] | Ziply Fiber |  | 18' 9"
[11 empty] | Lumen | 18' 9" | 17' 9"
[11 empty] | Lumen Downguy | 18' 9" | 17' 9"
2-1 | 46.0093 | -112.5381 | 35/4 | 0' | NWE | No | No | 8.9% | 10.4% | C | NWE Secondary Spool | 27' 8" | [5 empty] | Attach Ziply on j hook at 19'.
[11 empty] | Drip Loop | 26' 1"
[11 empty] | Ziply Fiber |  | 19' 0"
3-1 | 46.0086 | -112.538 | 30/7 | 0' | NWE | No | No | 7% | 7.2% | C | NWE Secondary Drop 1 | 24' 4" | [5 empty] | Attach Ziply on j hook at 18'.
[11 empty] | NWE Secondary Drop 2 | 23' 8"
[11 empty] | Drip Loop | 22' 9"
[11 empty] | Ziply Fiber |  | 18' 0"
4-1 | 46.008 | -112.5386 | 35/6 | 0' | NWE | No | No | 11.7% | 13.4% | C | NWE Secondary Drop | 28' 7" | [5 empty] | Attach Ziply on j hook at 18'.
[11 empty] | Drip Loop | 25' 10"
[11 empty] | Ziply Fiber |  | 18' 0"
5-1 | 46.0081 | -112.538 | 35/5 | 0' | NWE | No | No | 9.5% | 10.4% | C | NWE Secondary Drop | 29' 0" | [5 empty] | Attach Ziply on j hook at 18'.
[11 empty] | Drip Loop | 26' 4"
[11 empty] | Ziply Fiber |  | 18' 0"
6-1 | 46.0077 | -112.5386 | 30/7 | 0' | NWE | No | No | 11.5% | 14.1% | C | Street Light | 21' 9" | [5 empty] | Attach Ziply on j hook at 17'.
[11 empty] | NWE Secondary Drop | 21' 6"
[11 empty] | Drip Loop | 21' 4"
[11 empty] | Ziply Fiber |  | 17' 0"
7-1 | 46.0066 | -112.5386 | 30/7 | 0' | NWE | No | No | 14.2% | 12.6% | C | NWE Secondary Drop | 23' 8" | [5 empty] | Attach Ziply on j hook at 17'.
[11 empty] | Drip Loop | 22' 3"
[11 empty] | Ziply Fiber |  | 17' 0"
8-1 | 46.0114 | -112.5387 | 40/3 | 51' N 69' SW | NWE | No | No | 20.9% | 22.4% | C | NWE Secondary Drop 1 (SW) | 33' 1" |  | 24' 7" |  | 29' 1" | 29' 1" | Attach Ziply on j hook at 27'4" Retension and Sag Spectrum (SW).
[11 empty] | NWE Secondary Drop 2 (N) | 33' 1" |  | 27' 8" |  | 32' 6" | 33' 1"
[11 empty] | NWE Secondary Drop 2 (SW) | 33' 1" |  | 24' 7" |  | 26' 11" | 26' 11"
[11 empty] | NWE Secondary Drop 3 (N) | 33' 1" |  | 27' 0" |  | 32' 1" | 32' 7"
[11 empty] | NWE Secondary Drop 3 (SW) | 33' 1" |  | 20' 11" |  | 26' 6" | 26' 6"
[11 empty] | Drip Loop | 32' 7"
[11 empty] | Spectrum CATV (N) | 28' 4" |  | 24' 10" |  | 25' 6" | 25' 6"
[11 empty] | Spectrum CATV (SW) | 28' 4" |  | 19' 10" |  | 22' 11" | 22' 11"
[11 empty] | Ziply Fiber (N) |  | 27' 4" |  | 24' 6" | 24' 6" | 24' 6"
[11 empty] | Ziply Fiber (SW) |  | 27' 4" |  | 26' 4" | 26' 4" | 26' 4"
8-2 | 46.0116 | -112.5388 | 40/3 | 0' | NWE | No | No | 32.4% | 34.2% | C | NWE Secondary Drop 1 | 33' 9" | [5 empty] | Attach Ziply on j hook at 24'6"
[11 empty] | NWE Secondary Drop 2 | 33' 4"
[11 empty] | Drip Loop | 32' 4"
[11 empty] | NWE Riser 1 | 30' 6"
[11 empty] | NWE Riser 2 | 30' 6"
[11 empty] | Spectrum CATV | 25' 7"
[11 empty] | Ziply Fiber |  | 24' 6"
9-1 | 46.0114 | -112.5347 | [20 empty] | Laminated pole, unable to model using Ocalc. Will submit on later permit.
9-2 | 46.0113 | -112.5344 | 35/6 | 0' | NWE | No | No | 13.9% | 16.1% | C | Street Light | 27' 8" | [5 empty] | Attach Ziply on j hook at 20'.
[11 empty] | Street Light Drip | 26' 5"
[11 empty] | NWE Secondary Drop | 26' 10"
[11 empty] | Drip Loop | 26' 4"
[11 empty] | Ziply Fiber |  | 20' 0"
10-1 | 46.0117 | -112.5374 | 60/1 | 70' | NWE | No | No | 26.5% | 26.4% | C | NWE Primary Crossarm | 51' 7" |  | 33' 7" |  | 48' 7" | 49' 4" | "Lower Lumen to 21'10"" Attach Ziply on j hook at 22'10"""
[11 empty] | NWE Downguy | 50' 11"
[11 empty] | NWE Top Transformer | 47' 4"
[11 empty] | NWE Base Transformer | 43' 2"
[11 empty] | NWE Secondary Drop 1 | 42' 5" |  | 33' 5" |  | 35' 10" | 36' 7"
[11 empty] | NWE Secondary Drop 2 | 40' 9"
[11 empty] | Drip Loop | 39' 2"
[11 empty] | Spectrum CATV | 24' 2" |  | 20' 8" | 20' 0" | 20' 0" | 20' 0"
[11 empty] | Spectrum CATV Downguy | 24' 2"
[11 empty] | Ziply Fiber |  | 22' 10" |  | 19' 0" | 19' 0" | 19' 0"
[11 empty] | Lumen | 22' 10" | 21' 10"
10-2 | 46.0115 | -112.5373 | 30/5 | 155' S | NWE | No | No | 12.7% | 14.4% | C | NWE Riser | 26' 0" | [5 empty] | Raise Spectrum to 20' Attach Ziply on j hook at 19'" | "Tree Trim needed
[11 empty] | NWE Secondary Drop | 24' 6" |  | 26' 1" |  | 24' 6" | 24' 6"
[11 empty] | Drip Loop | 22' 7"
[11 empty] | Spectrum CATV | 18' 9" | 20' 0" | 20' 5" | 20' 0" | 20' 0" | 20' 0"
[11 empty] | Ziply Fiber |  | 19' 0" |  | 19' 0" | 19' 0" | 19' 0"
11-1 | 46.011 | -112.5372 | 30/7 | 100' N 81' S' | NWE | No | Yes/1 | 64.1% | 42.5% | C | NWE Span/Head | 22' 11" | [5 empty] | "Attach Ziply strand and downguy at 20'5"" Place Ziply anchor at 25' lead South and attach Ziply downguy. Optional: remove span guy to South, no longer needed"
[11 empty] | NWE Downguy |  | 22' 11"
[11 empty] | Spectrum CATV (N) | 21' 5" |  | 21' 0" | 21' 5" | 21' 5" | 21' 4"
[11 empty] | Spectrum CATV (S) | 21' 5" |  | 19' 9" | 21' 5" | 21' 5" | 21' 4"
[11 empty] | Spectrum CATV Downguy | 21' 7"
[11 empty] | Ziply Fiber (N) |  | 20' 5" |  | 20' 5" | 20' 5" | 20' 5"
[11 empty] | Ziply Fiber (S) |  | 20' 5" |  | 20' 0" | 20' 0" | 19' 11"
[11 empty] | Ziply Downguy |  | 20' 5"
11-2 | 46.0108 | -112.5373 | 45/3 | 95' | NWE | No | No | 21.9% | 24.9% | C | NWE Primary Crossarm | 36' 9" |  | 33' 3" |  | 32' 9" | 32' 11" | "Move Lumen from adjacent pole and attach at 21' Attach Ziply on j hook at 20'"
[11 empty] | NWE Downguy | 36' 2"
[11 empty] | NWE Top Transformer | 32' 11"
[11 empty] | NWE Base Transformer | 30' 3"
[11 empty] | NWE Neutral | 29' 0" |  | 25' 7" |  | 27' 0" | 27' 1"
[11 empty] | NWE Secondary Drop | 28' 3"
[11 empty] | Drip Loop | 26' 10"
[11 empty] | Spectrum CATV | 24' 8" | 22' 0" | 19' 8" | 20' 6" | 20' 6" | 20' 5"
[11 empty] | Lumen |  | 21' 0" | 17' 2" | 19' 4" | 19' 3" | 19' 2"
[11 empty] | Ziply Fiber |  | 20' 0" |  | 18' 0" | 18' 0" | 17' 11"
11-3 | 46.0105 | -112.5373 | 40/4 | 106' | NWE | No | No | 63.1% | 44.2% | C | NWE Primary Crossarm | 32' 11" |  | 31' 5" |  | 32' 1" | 32' 7" | Attach Ziply on j hook at 18'
[11 empty] | NWE Top Transformer | 30' 4"
[11 empty] | NWE Base Transformer | 27' 8"
[11 empty] | NWE Neutral | 27' 3" |  | 26' 9" |  | 27' 0" | 27' 1"
[11 empty] | Spool Insulator - 20 kV | 26' 7"
[11 empty] | NWE Secondary Drop | 26' 2" |  | 22' 0" |  | 24' 7" | 25' 6"
[11 empty] | Drip Loop | 23' 11"
[11 empty] | Spectrum CATV | 20' 6"
[11 empty] | Lumen | 19' 4"
[11 empty] | Lumen Sidewalk Guy | 19' 4"
[11 empty] | Ziply Fiber |  | 18' 0" |  | 18' 0" | 17' 11" | 17' 9"
11-4 | 46.0102 | -112.5372 | [15 empty] | Pole not needed. |  |  |  |  | Pole not needed.
12-1 | 46.0115 | -112.5361 | 40/4 | 51' N 59' S | NWE | No | Yes/1 | 81.2% | 34.8% | C | NWE Secondary Drop | 33' 3" |  | 31' 6" |  | 33' 0" | 33' 0" | "Attach Ziply at 21' 05"", slack to North Place Ziply downguy at 15' lead North and attach Ziply downguy"
[11 empty] | Drip Loop | 30' 5"
[11 empty] | NWE Riser | 31' 11"
[11 empty] | Spectrum CATV (N) | 22' 5" |  | 20' 10" |  | 21' 9" | 21' 9"
[11 empty] | Spectrum CATV (S) | 22' 5" |  |  |  | 22' 5" | 22' 5"
[11 empty] | Ziply Fiber (N) |  | 21' 5" |  | 20' 0" | 20' 0" | 20' 0"
[11 empty] | Ziply Fiber (S) |  | 21' 5" |  | 21' 5" | 21' 5" | 21' 5"
[11 empty] | Ziply Downguy |  | 21' 5"
12-2 | 46.0116 | -112.5361 | 45/2 | 67' | NWE | No | No | 25.9% | 18.1% | C | NWE Secondary Drop | 37' 3" |  | 29' 11" |  | 33' 7" | 33' 8" | Attach Ziply at 20'
[11 empty] | Drip Loop | 34' 8"
[11 empty] | Street Light | 33' 9"
[11 empty] | Spectrum CATV 1 | 23' 5" |  | 19' 9" |  | 21' 7" | 21' 7"
[11 empty] | Spectrum CATV 2 | 21' 9"
[11 empty] | Ziply Fiber |  | 20' 0" |  | 19' 11" | 19' 10" | 19' 8"
12-3 | 46.0115 | -112.5364 | 40/5 | 0' | NWE | No | Yes/1 | 78.3% | 64% | C | NWE Secondary Drop | 33' 8" | [5 empty] | "Attach Ziply on j hook at 20' | Place 1/4 EHS span guy at 32' running SW to F1R1 1-74"
[11 empty] | Drip Loop | 31' 4"
[11 empty] | NWE Span/Head |  | 32' 0"
[11 empty] | Spectrum CATV | 23' 7"
[11 empty] | Ziply Fiber |  | 20' 0"
13-1 | 46.0116 | -112.5348 | 50/2 | 38' | NWE | No | No | 21% | 21.7% | C | NWE Primary Crossarm | 41' 11" |  | 38' 7" |  | 39' 4" | 39' 5" | Attach Ziply on j hook at 22'4"
[11 empty] | NWE Top Transformer | 37' 5"
[11 empty] | NWE Base Transformer | 34' 5"
[11 empty] | NWE Secondary Drop | 32' 1" |  | 29' 5" |  | 30' 5" | 30' 5"
[11 empty] | Drip Loop | 30' 1"
[11 empty] | Spool Insulator | 30' 11"
[11 empty] | Spectrum CATV | 23' 4" |  | 22' 6" |  | 23' 4" | 23' 4"
[11 empty] | Ziply Fiber |  | 22' 4" |  | 22' 4" | 22' 4" | 22' 4"
13-2 | 46.0117 | -112.5348 | 50/2 | 41' | NWE | No | No | 60.2% | 61.5% | C | NWE Primary Crossarm 1 | 42' 6" |  | 40' 3" |  | 40' 11" | 41' 2" | Attach Ziply on j hook at 22'9"
[11 empty] | NWE Primary Crossarm 2 | 39' 5"
[11 empty] | Street Light | 31' 1"
[11 empty] | NWE Secondary Drop | 30' 6"
[11 empty] | Drip Loop | 29' 2"
[11 empty] | Spectrum CATV 1 | 24' 3" |  | 22' 6" |  | 22' 5" | 22' 5"
[11 empty] | Spectrum CATV 2 | 23' 9"
[11 empty] | Ziply Fiber |  | 22' 9" |  | 21' 5" | 21' 5" | 21' 5"
13-3 | 46.0117 | -112.5346 | 50/2 | 66' | NWE | No | No | 40.9% | 40.7% | C | NWE Primary Crossarm | 41' 2" |  | 42' 4" |  | 40' 8" | 41' 2" | "Attach Ziply on j hook at 21'5"" | Upgrade primary crossarm to fiberglass Uprate NWE downguys to 3/8 EHS"
[11 empty] | NWE Downguy | 40' 3"
[11 empty] | NWE Downguy | 39' 9"
[11 empty] | NWE Secondary Drop 1 | 35' 6" |  | 29' 5" |  | 33' 4" | 33' 7"
[11 empty] | NWE Secondary Drop 2 | 34' 6" |  | 28' 3" |  | 32' 5" | 32' 8"
[11 empty] | Drip Loop | 32' 6"
[11 empty] | Spectrum CATV | 22' 5" |  | 21' 6" | 22' 0" | 22' 0" | 21' 11"
[11 empty] | Spectrum Downguy | 22' 5"
[11 empty] | Ziply Fiber |  | 21' 5" |  | 21' 0" | 21' 0" | 21' 0"
13-4 | 46.0117 | -112.5344 | 50/2 | 78' | NWE | No | No | 27.1% | 27.6% | C | NWE Primary Crossarm | 42' 8" |  | 44' 2" |  | 43' 0" | 43' 6" | Attach Ziply on j hook at 21'
[11 empty] | NWE Top Transformer | 38' 9"
[11 empty] | NWE Base Transformer | 35' 9"
[11 empty] | NWE Secondary Drop 1 | 33' 7"
[11 empty] | NWE Secondary Drop 2 | 32' 8"
[11 empty] | NWE Secondary Drop 3 | 30' 1" |  | 31' 4" |  | 30' 1" | 30' 1"
[11 empty] | Drip Loop | 28' 11"
[11 empty] | Spectrum CATV | 22' 0" |  | 20' 10" |  | 21' 1" | 21' 1"
[11 empty] | Ziply Fiber |  | 21' 0" |  | 20' 0" | 20' 0" | 19' 11"
13-5 | 46.0118 | -112.5341 | 55/2 | 123' | NWE | No | No | 29.5% | 30.1% | C | NWE Primary Crossarm | 45' 11" |  | 46' 9" |  | 44' 9" | 46' 5" | Attach Ziply on j hook at 20'
[11 empty] | NWE Top Transformer | 42' 4"
[11 empty] | NWE Base Transformer | 39' 2"
[11 empty] | NWE Secondary Drop | 38' 2" |  | 29' 11" |  | 33' 6" | 34' 0"
[11 empty] | Drip Loop | 35' 6"
[11 empty] | Spectrum CATV | 21' 2" |  | 21' 0" |  | 21' 2" | 21' 1"
[11 empty] | Ziply Fiber |  | 20' 0" |  | 20' 0" | 20' 0" | 19' 10"
13-6 | 46.0118 | -112.5336 | 55/2 | 116' | NWE | No | No | 22.5% | 23% | C | NWE Primary Crossarm | 46' 6" |  | 43' 2" |  | 40' 6" | 42' 6" | Attach Ziply on j hook at 22'
[11 empty] | NWE Secondary Drop | 34' 1"
[11 empty] | Drip Loop | 32' 6"
[11 empty] | Spectrum CATV | 23' 10" |  | 22' 2" |  | 21' 3" | 21' 1"
[11 empty] | Ziply Fiber |  | 22' 0" |  | 20' 0" | 20' 0" | 19' 8"
13-7 | 46.0118 | -112.5331 | 40/1 | 66' | NWE | No | No | 7.6% | 8.4% | C | NWE Secondary Drop | 29' 10" |  | 29' 6" |  | 29' 8" | 29' 10" | Attach Ziply on j hook at 20'
[11 empty] | Drip Loop | 28' 7"
[11 empty] | Street Light 1 | 26' 10"
[11 empty] | Street Light 2 | 25' 9"
[11 empty] | Street Light Drip 1 | 26' 1"
[11 empty] | Street Light Drip 2 | 25' 5"
[11 empty] | Spectrum CATV | 21' 3" |  | 21' 9" |  | 21' 3" | 21' 3"
[11 empty] | Ziply Fiber |  | 20' 0" |  | 20' 0" | 20' 0" | 20' 0"
13-8 | 46.0118 | -112.5329 | 50/2 | 0' | NWE | No | No | 46.2% | 43.6% | C | NWE Primary Crossarm | 42' 3" | [5 empty] | Attach Ziply on j hook at 22'
[11 empty] | NWE Top Transformer | 37' 8"
[11 empty] | NWE Base Transformer | 35' 0"
[11 empty] | NWE Secondary Drop 1 | 32' 7"
[11 empty] | NWE Secondary Drop 2 | 31' 7"
[11 empty] | Drip Loop | 30' 5"
[11 empty] | Street Light | 30' 4"
[11 empty] | Street Light Drip | 30' 2"
[11 empty] | TDS | 24' 6"
[11 empty] | TDS Downguy | 24' 6"
[11 empty] | Spectrum CATV | 23' 10"
[11 empty] | Ziply Fiber |  | 22' 0"